# Tamil Nadu Health Systems Project

Progress of Procurement Plan

World Bank Mission

December 2011

# LIST OF ACTIVITIES / PROGRAMMES

ANNEX 1 : 		PROCUREMENT SCHEDULE FOR CIVIL WORKS

Construction of 4th floor and 5th  floor over the existing DMS Annexe Building

Construction of Maternity Block for Medical College Hospital,  Chengalpattu

Construction of Maternity Block for Medical College Hospital, Coimbatore

Construction of Maternity Block for Medical College Hospital, Thanjavur

Construction of Maternity Block for Medical College Hospital, Theni

Construction of Maternity Block for Medical College Hospital, Thoothukudi

Construction of Maternity Block for Medical College Hospital, Tiruchi

Construction of Maternity Block for Medical College Hospital, Tirunelveli

Construction of Maternity Block for Medical College Hospital, Vellore

ANNEX 2 : 		PROCUREMENT SCHEDULE FOR GOODS

Ambulance Services

Mortuary Van Services

Tribal Development Initiatives

Infection Control and Waste Management

Equipments – ICU / PICU

Cardio Vascular Disease & Diabetics Mellitus

Cancer Cervical / Cancer Breast

IEC Activities

HMS & HMIS thro ELCOT

CEmONC Services

Rationalization of Lab Services

Poison Treatment Centers

ANNEX 3 : 		PROCUREMENT SCHEDULE FOR NON-CONSULTANCY

ANNEX 4 : 		PROCUREMENT SCHEDULE FOR CONSULTANCY

# Tamil Nadu Health Systems Project – Additional Financing

Procurement Plan

## General

- Project information:

  - Project Name:  Tamil Nadu Health Systems Project– Additional Financing

  - Country:  India

  - Project Code:  P118830

- Bank’s approval Date of the procurement Plan: Draft Procurement Plan dated January xx, 2010 Revision 0 agreed by the Bank on January xx, 2010

- Date of General Procurement Notice: September 5, 2004

- Period covered by this procurement plan: 2 years (2010/11 and 2011/12)

- Risk Rating for the Implementing Agencies: Moderate

- Original Procurement Risk Rating for the Project: Substantial

- Current Procurement Risk Rating for the Project: Substantial (no change in original risk rating)

##### II. Goods and Works and non-consulting services.

1 a) Procurement Methods and Thresholds

| Category | Method of Procurement | Threshold (US$ Equivalent) |
| --- | --- | --- |
| Civil Works | International Competitive Bidding (ICB) | >5,000,000 |
|  | National Competitive Bidding (NCB) | Up to 5,000,000 |
|  | Shopping | Up to 30,000 |
|  | Direct Contracting (DC) | As per paragraph 3.6 of Guidelines (GL) |
|  | Build, Operate, Transfer (BOT) Contract | As per paragraph 3.13(a) of GL |
|  | Force Account | As per paragraph 3.8 of GL |
| Goods and Non-consultant services | International Competitive Bidding (ICB) | >600,000 |
|  | Limited International Bidding (LIB) | As per paragraph 3.2 of GL |
|  | National Competitive Bidding (NCB) | Up to 600,000 |
|  | Shopping | Up to 30,000 |
|  | Direct Contracting (DC) | As per paragraph 3.6 of GL |

1 b) Prior Review Threshold

Works: All contracts more than US$ 5.0 million equivalent (however the contracts identified in the Annex 1 will be prior reviewed by the Bank)

Goods: All contracts more than US$ 0.6 million equivalent

Services (other than consultancy): All contracts more than US$0.6 million equivalent

2.	Pre-qualification – If pre-qualification of bidders is required, the provisions of paragraphs 2.9 and 2.10 of the Guidelines will be used.

3.         Applicable Guidelines: All the contracts issued under the project will follow the World Bank’s Guidelines: Procurement under IBRD Loans and IDA Credits” dated May 2004 (updated in October 2006) and the provisions stipulated in the Loan and Project Agreements (to be read with Amendments, if any).

- Any Other Special Procurement Arrangements: Tamil Nadu Medical Services Corporation (TNMSC) shall be used as implementing agency for procurement of all the Goods under the Project. Electronics Corporation of Tamil Nadu Limited (ELCOT) will be used as Procurement Agent for handling the procurement of IT hardware and associated supplies/services and agreed management fee (2.5%) to ELCOT will be reimbursed from the Credit. For prior review contracts, the amendments for increasing the cost or extension of time beyond 15% of original value shall also be subject to Bank’s prior review. The provisions of paragraphs 2.55 and 2.56 of the Procurement Guidelines, providing for domestic preference in the evaluation of bids, shall apply to goods manufactured in the territory of the Borrower. National Competitive Bidding (NCB) will be conducted in accordance with paragraph 3.3 and 3.4 of the Guidelines and the following provisions:

  - Only the model bidding documents for NCB agreed with the GOI Task Force (and as amended for time to time), shall be used for bidding;

  - Invitations to bid shall be advertised in at least one widely circulated national daily newspaper, at least 30 days prior to the deadline for the submission of bids;

  - No special preference will be accorded to any bidder either for price or for other terms and conditions when competing with foreign bidders, state-owned enterprises, small-scale enterprises or enterprises from any given State;

  - Except with the prior concurrence of the Bank, there shall be no negotiation of price with the bidders, even with the lowest evaluated bidder;

  - Extension of bid validity shall not be allowed without the prior concurrence of the Bank (i) for the first request for extension if it is longer than four weeks; and (ii) for all subsequent requests for extension irrespective of the period (such concurrence will be considered by Bank only in cases of Force Majeure and circumstances beyond the control of the Purchaser/ Employer);

  - Re-bidding shall not be carried out without the prior concurrence of the Bank. The system of rejecting bids outside a pre-determined margin or "bracket" of prices shall not be used in the project;

  - Rate contracts entered into by Directorate General of Supplies and Disposals will not be acceptable as a substitute for NCB procedures. Such contracts will be acceptable however for any procurement under the Shopping procedures;

  - Two or three envelope system will not be used.

  - Any discount received from the bidders after bid submission deadline will not be considered either during the bid evaluation or the contract award.

  - Bids received from foreign bidders will not be rejected on the ground of nationality of the bidder

##### Procurement Packages with Methods and Time Schedule – Attached for Works and Goods (Annex 1 and 2) and Services other than consultancy (Annex 3).

##### III.     Selection of Consultants

1 a) Selection Methods and Thresholds

| Method of Procurement | Threshold (US$ Equivalent) |
| --- | --- |
| Selection Based on the Consultants’ Qualifications (CQS) | Up to 100,000, as per paragraph 3.7 of GL |
| Least-Cost Selection (LCS) | Up to 100,000, as per paragraph 3.6 of GL |
| Single-Source Selection (SSS) | As per paragraph 3.9-3.12 of GL |
| Selection of Individual consultants | As per paragraph 5.2 to 5.4 of GL |
| Selection under a Fixed Budget (FBS) | As per paragraph 3.1 and 3.5 of GL |
| Quality-Based Selection (QBS) | As per paragraph 3.1 and 3.2 of GL |
| Quality and Cost Based Selection (QCBS) | For remaining cases, as per Section II of GL |

1 b) Prior Review Threshold

Consultancy Services:	> US$200,000 equivalent for firms; and

> US$50,000 equivalent for individuals

In addition, all consultancy contracts to be issued on single-source basis exceeding US$ 50,000 in value to consultancy firms and US$ 25,000 to individual consultants shall be subject to prior review. In case of contract to individual consultants, the qualifications, experience, terms of reference and terms of employment shall be subject to prior review.

2.     Short list comprising entirely of national consultants: Short list of consultants for services, estimated to cost less than $ 500,000 equivalent per contract, may comprise entirely of national consultants in accordance with the provisions of paragraph 2.7 of the Consultant Guidelines.

- Any Other Special Selection Arrangements: For prior review contracts, the amendments for increasing the cost or extension of time beyond 15% of original value shall also be subject to Bank’s prior review.

- Applicable Guidelines: All the contracts issued under the project will follow the “Guidelines: Selection and Employment of Consultants by World Bank Borrowers” dated May 2004 (updated in October 2006) and the provisions stipulated in the Loan and Project Agreements (to be read with Amendments, if any).

- Consultancy Assignments with Selection Methods and Time Schedule - attached in Annex 4

##### IV.        Implementing Agency Capacity Building Activities with Time Schedule

| Action | To be completed by | Responsibility |
| --- | --- | --- |
| Training of all the staff in Bank procurement Procedures | All the existing procurement staff are already trained. If a new staff joins, the appropriate training should be arranged. | TNHSP PMU and TNMSC |

Annex 1: Procurement Schedule for Works

| Pkg.No. | Description | Method of Procurement | Estimated Cost (Million Rs.) | Prior or Post Review | Submission of Draft Bid Document to the Bank | No Objection for Bid documents by the World Bank | Publication of IFB in Newspapers and UNDB/ dg Market and beginning of sale of bid document | Receipt and Opening of Bids | Submission of BER to Bank for No Objection | Receipt of No Objection of Bank for BER | Signing of the contract | Contract Completed |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| CW-01 | Construction of 4th floor and 5th floor over the existing DMS Annexe Building, DMS Campus, CHENNAI | NCB | 45.00 | Post Review | N.A. | N.A. | 02.05.10 | 06.06.10 | N.A. | N.A. | 05.09.10 | 30.09.2011 |
|  |  | Revised | 45.00 | Post Review | N.A. | N.A. | 22.08.10 | 29.09.10 | N.A. | N.A. | 25.10.10 | 31.10.2011 |
|  |  | Revised | 45.00 | Post Review | N.A. | N.A. | 22.08.10 | 29.09.10 | N.A. | N.A. | 25.10.10 | 31.12.2011 |
| CW-02 | Construction of Maternity Block for Medical College Hospital, Chengalpattu | NCB | 60.00 | Prior Review | 15.04.10 | 25.04.10 | 03.05.10 | 10.06.10 | 15.07.10 | 25.07.10 | 09.09.10 | 31.12.2011 |
|  |  | Revised | 60.00 | Prior Review | 01.03.11 | 20.03.11 | 01.04.11 | 10.05.11 | 10.08.11 | 07.09.11 | 01.10.11 | 31.12.2012 |
|  |  | Revised | 60.00 | Prior Review | 12.05.11 | 20.06.11 | 01.07.11 | 09.08.11 | 10.10.11 | 17.10.11 | 01.11.11 | 31.01.2013 |
|  |  | Revised | 60.00 | Prior Review | 27.05.11 | 12.07.11 | 29.07.11 | 30.08.11 | 15.12.11 | 31.12.11 | 28.02.12 | 31.05.2013 |
| CW-03 | Construction of Maternity Block for Medical College Hospital, Coimbatore | NCB | 60.00 | Post Review | N.A. | N.A. | 04.05.10 | 11.06.10 | N.A. | N.A. | 10.09.10 | 31.12.2011 |
|  |  | Revised | 60.00 | Post Review | N.A. | N.A. | 15.02.11 | 01.04.11 | N.A. | N.A. | 01.08.11 | 31.10.2012 |
|  |  | Revised | 60.00 | Post Review | N.A. | N.A. | 01.07.11 | 10.08.11 | N.A. | N.A. | 30.11.11 | 28.02.2013 |
|  |  | Revised | 60.00 | Post Review | N.A. | N.A. | 24.08.11 | 28.09.11 | N.A. | N.A. | 31.01.12 | 30.04.2013 |
| CW-04 | Construction of Maternity Block for Medical College Hospital, Thanjavur | NCB | 60.00 | Post Review | N.A. | N.A. | 05.05.10 | 12.06.10 | N.A. | N.A. | 11.09.10 | 31.12.2011 |
|  |  | Revised | 60.00 | Post Review | N.A. | N.A. | 15.02.11 | 01.04.11 | N.A. | N.A. | 01.08.11 | 31.10.2012 |
|  |  | Revised | 60.00 | Post Review | N.A. | N.A. | 01.07.11 | 10.08.11 | N.A. | N.A. | 30.11.11 | 28.02.2013 |
|  |  | Revised | 60.00 | Post Review | N.A. | N.A. | 29.08.11 | 28.09.11 | N.A. | N.A. | 31.01.12 | 30.04.2013 |
| CW-05 | Construction of Maternity Block for Medical College Hospital, Theni | NCB | 60.00 | Post Review | N.A. | N.A. | 04.05.10 | 11.06.10 | N.A. | N.A. | 10.09.10 | 31.12.2011 |
|  |  | Revised | 60.00 | Post Review | N.A. | N.A. | 15.02.11 | 01.04.11 | N.A. | N.A. | 01.08.11 | 31.10.2012 |
|  |  | Revised | 60.00 | Post Review | N.A. | N.A. | 01.07.11 | 10.08.11 | N.A. | N.A. | 30.11.11 | 28.02.2013 |
|  |  | Revised | 60.00 | Post Review | N.A. | N.A. | 22.07.11 | 25.08.11 | N.A. | N.A. | 31.01.12 | 30.04.2013 |
| CW-06 | Construction of Maternity Block for Medical College Hospital, Thoothukudi | NCB | 60.00 | Post Review | N.A. | N.A. | 03.05.10 | 10.06.10 | N.A. | N.A. | 09.09.10 | 31.12.2011 |
|  |  | Revised | 60.00 | Post Review | N.A. | N.A. | 15.02.11 | 01.04.11 | N.A. | N.A. | 01.08.11 | 31.10.2012 |
|  |  | Revised | 60.00 | Post Review | N.A. | N.A. | 01.07.11 | 10.08.11 | N.A. | N.A. | 30.11.11 | 28.02.2013 |
|  |  | Revised | 60.00 | Post Review | N.A. | N.A. | 04.08.11 | 07.09.11 | N.A. | N.A. | 31.01.12 | 30.04.2013 |
| CW-07 | Construction of Maternity Block for Medical College Hospital, Tiruchi | NCB | 60.00 | Post Review | N.A. | N.A. | 05.05.10 | 12.06.10 | N.A. | N.A. | 11.09.10 | 31.12.2011 |
|  |  | Revised | 60.00 | Post Review | N.A. | N.A. | 15.02.11 | 01.04.11 | N.A. | N.A. | 01.08.11 | 31.10.2012 |
|  |  | Revised | 60.00 | Post Review | N.A. | N.A. | 01.07.11 | 10.08.11 | N.A. | N.A. | 30.11.11 | 28.02.2013 |
|  |  | Revised | 60.00 | Post Review | N.A. | N.A. | 05.08.11 | 07.09.11 | N.A. | N.A. | 31.01.12 | 30.04.2013 |
| CW-08 | Construction of Maternity Block for Medical College Hospital, Tirunelveli | NCB | 60.00 | Prior Review | 15.04.10 | 25.04.10 | 04.05.10 | 11.06.10 | 15.07.10 | 25.07.10 | 10.09.10 | 31.12.2011 |
|  |  | Revised | 60.00 | Prior Review | 01.03.11 | 20.03.11 | 01.04.11 | 10.05.11 | 10.08.11 | 07.09.11 | 01.10.11 | 31.12.2012 |
|  |  | Revised | 60.00 | Prior Review | 25.06.11 | 04.07.11 | 11.07.11 | 24.08.11 | 23.09.11 | 03.10.11 | 03.11.11 | 31.01.2013 |
|  |  | Revised | 60.00 | Prior Review | 17.08.11 | 25.08.11 | 02.09.11 | 12.10.11 | 15.12.11 | 31.12.11 | 28.02.12 | 31.05.2013 |
| CW-09 | Construction of Maternity Block for Medical College Hospital, Vellore | NCB | 60.00 | Post Review | N.A. | N.A. | 03.05.10 | 10.06.10 | N.A. | N.A. | 09.09.10 | 31.12.2011 |
|  |  | Revised | 60.00 | Post Review | N.A. | N.A. | 15.02.11 | 01.04.11 | N.A. | N.A. | 01.08.11 | 31.10.2012 |
|  |  | Revised | 60.00 | Post Review | N.A. | N.A. | 01.07.11 | 10.08.11 | N.A. | N.A. | 30.11.11 | 28.02.2013 |
|  |  | Revised | 60.00 | Post Review | N.A. | N.A. | 29.07.11 | 30.08.11 | N.A. | N.A. | 31.01.12 | 30.04.2013 |
|  | Total (INR) Million |  | 525.00 |  |  |  |  |  |  |  |  |  |

Annex 2: Procurement Schedule for Goods

| Package No. | Description | Method of Procurement | Estimated Cost (Million Rs.) | Prior or Post Review | Submission of Draft Bid Document to the Bank | No Objection for Bid documents by the World Bank | Publication of IFB in Newspapers and UNDB/ dgMarket and beginning of sale of bid document | Receipt and Opening of Bids | Submission of BER to Bank for No Objection | Receipt of No Objection of Bank for BER | Signing of the contract | Contract Completed |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 |
|  | Ambulance Services |  |  |  |  |  |  |  |  |  |  |  |
| AG1 | Emergency Ambulances base vehicle | ICB | 99.50 | Prior Review | 12/Oct/10 | 29/Oct/10 | 8/Nov/10 | 23/Dec/10 | 21/Feb/11 | 13/Mar/11 | 23/Mar/11 | 21/Jul/11 |
|  |  |  |  |  |  |  | 8/Nov/10 | 28/Jan/11 |  |  | 10/Aug/11 | 08/Dec/11 |
| AG1A | Fabrication for BLS | ICB | 68.00 | Prior Review | 12/Oct/10 | 29/Oct/10 | 8/Nov/10 | 23/Dec/10 | 21/Feb/11 | 13/Mar/11 | 23/Mar/11 | 21/Jul/11 |
|  |  |  |  |  |  |  | 8/Nov/10 | 1/Feb/11 | World Bank permission for negotiation/ retender. World bank suggests to go for retender with revised Related Services schedule. |
|  |  |  |  |  |  |  | 18/Aug/11 | 29/Sep/11 |  |  | 17/Nov/11 | 16/Mar/12 |
| AG1B | Emergency Small Ambulances base vehicle – (30 Vehicles) | NCB | 21.00 | Post Review | 5/Nov/11 | NA | 15/Nov/11 | 15/Dec/11 | 29/Jan/12 | NA | 8/Feb/12 | 8/May/12 |
|  |  |  |  |  |  |  |  |  | Bids Under preparation by TNMSC |
| AG1C | Fabrication for Small Ambulance – (30 Vehicles) | NCB | 12.00 | Post Review | 5/Nov/11 | NA | 15/Nov/11 | 15/Dec/11 | 29/Jan/12 | NA | 8/Feb/12 | 8/May/12 |
|  |  |  |  |  |  |  |  |  | Bids Under preparation by TNMSC |
| AG2_I | Auto Loader – Collapsible stretcher | NCB | 9.35 | Post Review | 2/Dec/11 | NA | 12/Dec/11 | 11/Jan/12 | 25/Feb/12 | NA | 6/Mar/12 | 4/Jun/12 |
|  | Scoop Stretcher |  |  |  |  |  |  |  |  |  |  |  |
|  | Spine board with straps and Head Blocks Rigid |  |  |  |  |  |  |  |  |  |  |  |
|  | Wheel chair |  |  |  |  |  |  |  |  |  |  |  |
| AG2_II | Oxygen Cylinder D Type | NCB | 6.73 | Post Review | 2/Dec/11 | NA | 12/Dec/11 | 11/Jan/12 | 25/Feb/12 | NA | 6/Mar/12 | 4/Jun/12 |
|  | Portable Oxygen Cylinder - Refillable |  |  |  |  |  |  |  |  |  |  |  |
|  | Oxygen Key(suitable for both D type and portable Oxygen Cylinder) |  |  |  |  |  |  |  |  |  |  |  |
| AG2_III | AC / DC / Foot Operated - Suction Pump | NCB | 5.65 | Post Review | 2/Dec/11 | NA | 12/Dec/11 | 11/Jan/12 | 25/Feb/12 | NA | 6/Mar/12 | 4/Jun/12 |
|  | Ambu Bag Adult –Silicon |  |  |  |  |  |  |  |  |  |  |  |
|  | Ambu Bag Child- Silicon |  |  |  |  |  |  |  |  |  |  |  |
|  | Mouth to Mask ventilation devise Adult |  |  |  |  |  |  |  |  |  |  |  |
|  | Mouth to Mask ventilation devise paediatric |  |  |  |  |  |  |  |  |  |  |  |
|  | Stethoscope |  |  |  |  |  |  |  |  |  |  |  |
|  | BP Apparatus (Digital) |  |  |  |  |  |  |  |  |  |  |  |
|  | BP Apparatus (Manual - Mercury ) |  |  |  |  |  |  |  |  |  |  |  |
|  | BP Cuff Pediatric (manual) |  |  |  |  |  |  |  |  |  |  |  |
|  | Pupillary Torch |  |  |  |  |  |  |  |  |  |  |  |
|  | Needle & Syringe Destroyer |  |  |  |  |  |  |  |  |  |  |  |
|  | Thermometer (Digital) |  |  |  |  |  |  |  |  |  |  |  |
|  | Fingertip Pulse Oxy meter: |  |  |  |  |  |  |  |  |  |  |  |
| AG2_IV | Nebuliser | NCB | 3.61 | Post Review | 2/Dec/11 | NA | 12/Dec/11 | 11/Jan/12 | 25/Feb/12 | NA | 6/Mar/12 | 4/Jun/12 |
|  | Kidney Tray |  |  |  |  |  |  |  |  |  |  |  |
|  | Urine Pan ( Male and Female) |  |  |  |  |  |  |  |  |  |  |  |
|  | Bed Pan (Unbreakable autoclavable) |  |  |  |  |  |  |  |  |  |  |  |
|  | Disposable Sputum Cup |  |  |  |  |  |  |  |  |  |  |  |
|  | Gluco Lancets |  |  |  |  |  |  |  |  |  |  |  |
| AG2_V | 12" Wrench Adjustable Open End | NCB | 2.50 | Post Review | 2/Dec/11 | NA | 12/Dec/11 | 11/Jan/12 | 25/Feb/12 | NA | 6/Mar/12 | 4/Jun/12 |
|  | 12" Screw Driver Standard Square Bar |  |  |  |  |  |  |  |  |  |  |  |
|  | 8" Screw Driver Philips Head # 2 |  |  |  |  |  |  |  |  |  |  |  |
|  | Hacksaw with 12" Carbide Wire Blade |  |  |  |  |  |  |  |  |  |  |  |
|  | Vise Grip Pliers 10" |  |  |  |  |  |  |  |  |  |  |  |
|  | 5lb Hammer with 15" Handle |  |  |  |  |  |  |  |  |  |  |  |
|  | Fire Axe Butt 24" Handle |  |  |  |  |  |  |  |  |  |  |  |
|  | Wrecking Bar with 24" Handle |  |  |  |  |  |  |  |  |  |  |  |
|  | 51" Crowbar Pinch Point |  |  |  |  |  |  |  |  |  |  |  |
|  | Bolt Cutter with 1" To ¼" Jaw Opening |  |  |  |  |  |  |  |  |  |  |  |
|  | Showel with Pointed Blade |  |  |  |  |  |  |  |  |  |  |  |
|  | Tin Snips - Double Action 8" Minimum |  |  |  |  |  |  |  |  |  |  |  |
|  | Gauntlets |  |  |  |  |  |  |  |  |  |  |  |
|  | Ropes 5400lb Tensile Strength in 50' Length in Bag |  |  |  |  |  |  |  |  |  |  |  |
|  | Mastic Knife |  |  |  |  |  |  |  |  |  |  |  |
|  | Spring Load Center Punch |  |  |  |  |  |  |  |  |  |  |  |
|  | Goggles |  |  |  |  |  |  |  |  |  |  |  |
|  | Pruning Saw |  |  |  |  |  |  |  |  |  |  |  |
|  | Fire Extinguisher – 5kg ABC based |  |  |  |  |  |  |  |  |  |  |  |
|  | AC/DC Rechargeable Luminous search light |  |  |  |  |  |  |  |  |  |  |  |
|  | Splints |  |  |  |  |  |  |  |  |  |  |  |
|  | Roller Splints |  |  |  |  |  |  |  |  |  |  |  |
|  | Cervical Collars |  |  |  |  |  |  |  |  |  |  |  |
|  | Mortuary van services |  |  |  |  |  |  |  |  |  |  |  |
| AG3 | Procurement of Mortuary vehicles | NCB | 14.70 | Post Review | 22/Oct/10 | NA | 5/Feb/11 | 7/Mar/11 | 21/Apr/11 | NA | 1/May/11 | 30/Jul/11 |
|  |  |  |  |  |  |  | 1/Feb/11 |  | No Response, Retender floated. |
|  |  |  |  |  |  |  | 5/Jul/11 | 02/Sep/11 |  |  | 21/Nov/11 | 19/Feb/12 |
| AG4 | Procurement of freezer box | NCB | 2.10 | Post Review | 22/Oct/10 | NA | 5/Feb/11 | 7/Mar/11 | 21/Apr/11 | NA | 1/May/11 | 30/Jul/11 |
|  |  |  |  |  |  |  | 1/Feb/11 |  | No Response. Retender floated. |
|  |  |  |  |  |  |  | 5/Jul/11 | 16/Aug/11 | Board recommended for procurement of freezer box single body (instead of two bodies). NOC received from WB and Re-tender to be floated by TNMSC. |
|  | Tribal Development Initiatives |  |  |  |  |  |  |  |  |  |  |  |
| AG5 | Additional Mobile Out Reach Services (Vehicle) | NCB | 6.00 | Post Review | 22/Oct/10 | NA | 29/Dec/10 | 28/Jan/11 | 14/Mar/11 | NA | 24/Mar/11 | 22/Jun/11 |
|  |  |  |  |  |  |  | 2/Feb/11 |  | No response; retender floated. |
|  |  |  |  |  |  |  | 5/Jul/11 | 30/Aug/11 | WB has said DGS&D rate contract is not applicable for NCB procedure. The method approved in the procurement plan to be followed. Order put-up for MD, TNMSC approval. |
| AG6 | Equipments for Out Reach Services (Vehicle) | NS | 0.80 | Post Review | 22/Oct/10 | NA | 29/Dec/10 | 13/Jan/11 | 12/Feb/11 | NA | 22/Feb/11 | 23/Apr/11 |
|  |  |  |  |  |  |  | Limited Tender to be floated after arrival of vehicle and getting detailed specification from the Project. |
| AG7 | TV Sets for mobile outreach vans and DVD player including Installation | NS | 0.40 | Post Review | 22/Oct/10 | NA | 29/Dec/10 | 13/Jan/11 | 12/Feb/11 | NA | 22/Feb/11 | 23/Apr/11 |
|  |  |  |  |  |  |  | Limited Tender to be floated along with equipments under package 6 above. |
|  | Infection Control and Waste Management |  |  |  |  |  |  |  |  |  |  |  |
| AG8 | Hand books for the training on Infection Control and Waste Management | NCB | 7.50 | Post Review | 26/Dec/10 | NA | 5/Feb/11 | 7/Mar/11 | 21/Apr/11 | NA | 1/May/11 | 30/Jul/11 |
|  | Equipments - ICU / PICU |  |  |  |  |  |  |  |  |  |  |  |
| AG9 | Digital X-Ray (one per District) | ICB | 201.50 | Prior Review | 16/Mar/11 | 29/Oct/10 | 8/Nov/10 | 24/Dec/10 | 22/Feb/11 | 14/Mar/11 | 24/Mar/11 | 22/Jul/11 |
|  |  |  |  |  |  |  | 08/Nov/10 | 14/Jun/11 | BER Sent to WB on 07/11/11. Clarification reply from TNMSC to WB |
| AG10 | Echo-Cardiogram - Non cvd program district | ICB | 30.00 | Prior Review | 16/Mar/11 | 2/Dec/10 | 8/Dec/10 | 27/Jan/11 | 28/Mar/11 | 17/Apr/11 | 27/Apr/11 | 25/Aug/11 |
|  |  |  |  |  |  |  | 08/Dec/10 | 20/Apr/11 |  |  | 12/Aug/11 | 10/Dec/11 |
| AG11 | Modular - Multipara Monitor | ICB | 40.00 | Prior Review | 16/Mar/11 | 3/Dec/10 | 8/Dec/10 | 25/Jan/11 | 26/Mar/11 | 15/Apr/11 | 25/Apr/11 | 23/Aug/11 |
|  |  |  |  |  |  |  | 08/Dec/10 | 12/Apr/11 | Order put-up for MD, TNMSC approval. |
| AG12 | Replacement of Old / Unsafe X-Ray units with CR units | ICB | 45.00 | Prior Review | 16/Mar/11 | 26/Mar/11 | 5/Apr/11 | 20/May/11 | 19/Jul/11 | 8/Aug/11 | 18/Aug/11 | 16/Dec/11 |
|  |  |  |  |  |  |  | Tender to be floated after finalizing about mammogram |
| AG13 | ICU Cots with Matresses | NCB | 5.20 | Post Review | 26/Mar/11 | NA | 5/Apr/11 | 5/May/11 | 19/Jun/11 | NA | 29/Jun/11 | 27/Sep/11 |
|  |  |  |  |  |  |  | 21/Feb/11 | 23/Mar/11 |  |  | 12/Aug/11 | 10/Nov/11 |
| AG14 | Pulse Oximeter (Adult & Pediotric probe) | NCB | 5.53 | Post Review | 26/Mar/11 | NA | 5/Apr/11 | 5/May/11 | 19/Jun/11 | NA | 29/Jun/11 | 27/Sep/11 |
|  |  |  |  |  |  |  | 2/Feb/11 | 18/Mar/11 | L3 bidder raised objection on CE& USFDA. When referred WB not willing to give opinion. Retendered with revised qualification criteria. |
|  |  |  |  |  |  |  | 18/Oct/11 | 17/Nov/11 | Under Evaluation ( 5 Bids Received) |
| AG15 | Syringe Infusion Pump | NCB | 7.55 | Post Review | 26/Mar/11 | NA | 5/Apr/11 | 5/May/11 | 19/Jun/11 | NA | 29/Jun/11 | 27/Sep/11 |
|  |  |  |  |  |  |  | 7/Feb/11 | 18/Mar/11 |  |  | 01/Jul/11 | 29/Sep/11 |
| AG16 | Volume Infusion Pump | NCB | 6.75 | Post Review | 26/Mar/11 | NA | 5/Apr/11 | 5/May/11 | 19/Jun/11 | NA | 29/Jun/11 | 27/Sep/11 |
|  |  |  |  |  |  |  | 7/Feb/11 | 9/Mar/11 |  |  | 01/Jul/11 | 29/Sep/11 |
| AG17 | AED Defibrillator | ICB | 72.00 | Prior Review | 16/Mar/11 | 2/Dec/10 | 8/Dec/10 | 27/Jan/11 | 28/Mar/11 | 17/Apr/11 | 27/Apr/11 | 25/Aug/11 |
|  |  |  |  |  |  |  | 8/Dec/10 | 17/Feb/11 | Clarification on the bid quoted by L1 (Philips) without indicating customs duty was furnished. Re-Tendered. |
|  |  |  |  |  |  |  | 12/Oct/11 | 11/Nov/11 | Under evaluation (3 Bids received) |
| AG18 | A/C Units 2 ton | NCB | 5.97 | Post Review | 26/Mar/11 | NA | 5/Apr/11 | 5/May/11 | 19/Jun/11 | NA | 29/Jun/11 | 27/Sep/11 |
|  |  |  |  |  |  |  | 8/Feb/11 | 10/Mar/11 | The tender committee approved for re-tender with revised qualification criteria in consultation with the PD, TNHSP. Retender floated. |
|  |  |  |  |  |  |  | 2/Aug/11 | 2/Sep/11 | Procurement of this item either from DGS&D or by finalizing the lowest rate through a rate contract tender invited among manufacturer and installation by their local dealers. Retender floated |
|  |  |  |  |  |  |  | 14/Nov/11 | 14/Dec/11 |  |  |  |  |
| AG19 | ABG Analyzer | NCB | 6.00 | Post Review | 26/Mar/11 | NA | 5/Apr/11 | 5/May/11 | 19/Jun/11 | NA | 29/Jun/11 | 27/Sep/11 |
|  |  |  |  |  |  |  | 8/Feb/11 | 17/Jun/11 | Dropped. |
| AG20 | Dialysis Machine with RO Plant (2 per District) | ICB | 28.90 | Prior Review | 16/Mar/11 | 3/Dec/10 | 8/Dec/10 | 28/Jan/11 | 29/Mar/11 | 18/Apr/11 | 28/Apr/11 | 26/Aug/11 |
|  |  |  |  |  |  |  | 8/Dec/10 | 29/Mar/11 | The single bidder could be considered for acceptance. But the WB in their message dated 1/11/11 did not agreed. Retender with revised qualification NOC received from WB on 29/11/11. |
| AG21 | Computerized ECG | NCB | 5.60 | Post Review | 26/Mar/11 | NA | 5/Apr/11 | 5/May/11 | 19/Jun/11 | NA | 29/Jun/11 | 27/Sep/11 |
|  |  |  |  |  |  |  | 9/Feb/11 | 11/Mar/11 |  |  | 22/Aug/11 | 20/Nov/11 |
|  | Cardio vascular disease |  |  |  |  |  |  |  |  |  |  |  |
| AG22 | Echo-Cardiogram | ICB | 30.00 | Prior Review | 18/Aug/10 | 2/Dec/10 | 8/Dec/10 | 27/Jan/11 | 28/Mar/11 | 17/Apr/11 | 27/Apr/11 | 25/Aug/11 |
|  |  |  |  |  |  |  | 08/Dec/10 | 20/Apr/11 |  |  | 12/Aug/11 | 10/Dec/11 |
| AG23 | Semi Auto Analyser - 1 in each of 200 facilities +100 Municipal Hospitals (with 3 Micropippette and UPS) | NCB | 12.00 | Post Review | 28/Aug/10 | NA | 5/Jan/11 | 4/Feb/11 | 21/Mar/11 | NA | 31/Mar/11 | 29/Jun/11 |
|  |  |  |  |  |  |  | 1/Mar/11 | 1/Apr/11 |  |  | 29/Apr/11 | 28/Jul/11 |
| AG24 | Weighing Machine - 1 in 270 Hospitals, 1539 PHCs +100 Municipal Hospitals | NCB | 1.25 | Post Review | 27/Oct/10 | NA | 28/Dec/10 | 27/Jan/11 | 13/Mar/11 | NA | 23/Mar/11 | 21/Jun/11 |
|  |  |  |  |  |  |  | 9/Feb/11 | 11/Mar/11 | No response. Retender floated with revised qualification criteria. |
|  |  |  |  |  |  |  | 05/Jul/11 | 05/Aug/11 | Both the bidders are non responsive on BIS Standard. Retendered. |
|  |  |  |  |  |  |  | 8/Nov/11 | 23/Nov/11 | Under evaluation |
| AG25 | Stadiometer - 1 in 270 Hospitals, 1539 PHCs +100 Municipal Hospitals (measuring tape included) | NS | 1.67 | Post Review | 28/Aug/10 | NA | 28/Dec/10 | 12/Jan/11 | 11/Feb/11 | NA | 21/Feb/11 | 22/Apr/11 |
|  |  |  |  |  |  |  | 02/Aug/11 | 16/Aug/11 |  |  | 04/Oct/11 | 03/Dec/11 |
| AG26 | BP Apparatus - 2 in 270 Hospitals, 1539 PHCs +100 Municipal Hospitals | NCB | 2.67 | Post Review | 28/Aug/10 | NA | 28/Dec/10 | 27/Jan/11 | 13/Mar/11 | NA | 23/Mar/11 | 21/Jun/11 |
|  |  |  |  |  |  |  | 14/Feb/11 | 16/Mar/11 | Both the bidders were non responsive. Retender floated with revised qualification criteria. |
|  |  |  |  |  |  |  | 10/Aug/11 | 23/Nov11 | Under evaluation |
| AG27 | ECG Machine - 1 in each of 100 facilities+100 Municipal Hospital | NCB | 4.00 | Post Review | 28/Aug/10 | NA | 5/Jan/11 | 4/Feb/11 | 21/Mar/11 | NA | 31/Mar/11 | 29/Jun/11 |
|  |  |  |  |  |  |  | 14/Feb/11 | 16/Mar/11 |  |  | 04/Jul/11 | 02/Oct/11 |
| AG28 | Furniture (racks to keep CVD files/ HT ID Cards) in PHCs (1539) and 270 Hospitals | NCB | 14.20 | Post Review | 28/Aug/10 | NA | 28/Dec/10 | 27/Jan/11 | 13/Mar/11 | NA | 23/Mar/11 | 21/Jun/11 |
|  |  |  |  |  |  |  | 15/Feb/11 | 17/Mar/11 | Re-tender only for steel cupboard with revised qualification criteria. |
|  |  |  |  |  |  |  | 18/Oct/11 | 2/Dec/11 |  |
| AG29A | Printing of Booklets, Forms and Stationaries, etc ( Year 2010-11) | NCB | 19.28 | Post Review | 28/Aug/10 | NA | 31/Jan/11 | 2/Mar/11 | 16/Apr/11 | NA | 26/Apr/11 | 25/Jul/11 |
|  |  |  |  |  |  |  | Bid Documents send to TNMSC on 02/12/11. |
| AG29B | Printing of Booklets, Forms and Stationaries, etc ( Year 2011-12) | NCB | 3.19 | Post Review | 28/Aug/11 | NA | 5/Oct/11 | 4/Nov/11 | 19/Dec/11 | NA | 29/Dec/11 | 28/Mar/12 |
| AG29C | Printing of Booklets, Forms and Stationaries, etc ( Year 2012-13) | NCB | 3.19 | Post Review | 28/Aug/12 | NA | 5/Oct/12 | 4/Nov/12 | 19/Dec/12 | NA | 29/Dec/12 | 29/Mar/13 |
|  | Cardio vascular disease (NEW PACKAGES) |  |  |  |  |  |  |  |  |  |  |  |
| AG29D | ECG Paper / Rolls (Year 2011 – 2012) budgeted only for the first year of the programe | NCB | 15.89 | Post Review | 18/Feb/11 | NA | 28/Feb/11 | 30/Mar/11 | 14/May/11 | NA | 24/May/11 | 22/Aug/11 |
|  |  |  |  |  |  |  | On Hold. Tender will be floated based on the requirement/usage of ECG paper rolls. |
| AG29E | Centrifuge Machine with 6 Buckets 1 in 270 hospitals , 1539 PHCs +100 Municipal Hospitals | NCB | 9.55 | Post Review | 26/Dec/10 | NA | 5/Jan/11 | 4/Feb/11 | 21/Mar/11 | NA | 31/Mar/11 | 29/Jun/11 |
|  |  |  |  |  |  |  | 1/Mar/11 | 17/May/11 |  |  | 04/Oct/11 | 02/Jan/12 |
| AG29F | Glass Test Tubes ( 1 Unit of 30 glass test tubes ) 1 unit in each of 100 Municipal Hospitals ( Year 2010-11) | NS | 0.01 | Post Review | 18/Feb/11 | NA | 28/Feb/11 | 15/Mar/11 | 14/Apr/11 | NA | 24/Apr/11 | 23/Jun/11 |
|  |  |  |  |  |  |  | 02/Aug/11 | 16/Aug/11 |  |  | 26/Sep/11 | 25/Nov/11 |
| AG29G | Glass Test Tubes ( 1 Unit of 30 glass test tubes ) 1 unit in each of 100 Municipal Hospitals ( Year 2011-12) | NS | 0.01 | Post Review | 31/Jul/11 | NA | 10/Aug/11 | 25/Aug/11 | 24/Sep/11 | NA | 4/Oct/11 | 3/Dec/11 |
| AG29H | Glass Test Tubes ( 1 Unit of 30 glass test tubes ) 1 unit in each of 100 Municipal Hospitals ( Year 2012-13) | NS | 0.01 | Post Review | 31/Jul/12 | NA | 10/Aug/12 | 25/Aug/12 | 24/Sep/12 | NA | 4/Oct/12 | 3/Dec/12 |
| AG29I | Micropippette tips for taking reagents (1 Unit of 1000 tips ) 1 units in each of 100 Municipal Hospitals ( Year 2010-11) | NS | 0.04 | Post Review | 18/Feb/11 | NA | 28/Feb/11 | 15/Mar/11 | 14/Apr/11 | NA | 24/Apr/11 | 23/Jun/11 |
|  |  |  |  |  |  |  | 02/Aug/11 | 16/Aug/11 |  |  | 23/Sep/11 | 22/Nov/11 |
| AG29J | Micropippette tips for taking reagents (1 Unit of 1000 tips ) 1 units in each of 100 Municipal Hospitals ( Year 2011-12) | NS | 0.04 | Post Review | 31/Jul/11 | NA | 10/Aug/11 | 25/Aug/11 | 24/Sep/11 | NA | 4/Oct/11 | 3/Dec/11 |
| AG29K | Micropippette tips for taking reagents (1 Unit of 1000 tips ) 1 units in each of 100 Municipal Hospitals ( Year 2012-13) | NS | 0.04 | Post Review | 31/Jul/12 | NA | 10/Aug/12 | 25/Aug/12 | 24/Sep/12 | NA | 4/Oct/12 | 3/Dec/12 |
| AG29L | Micropippette tips for taking samples reagents (1 Unit of 1000 tips ) 1 units in each of 100 Municipal Hospitals ( Year 2010-11) | NS | 0.03 | Post Review | 18/Feb/11 | NA | 28/Feb/11 | 15/Mar/11 | 14/Apr/11 | NA | 24/Apr/11 | 23/Jun/11 |
|  |  |  |  |  |  |  | 02/Aug/11 | 16/Aug/11 |  |  | 08/Sep/11 | 07/Nov/11 |
| AG29M | Micropippette tips for taking samples reagents (1 Unit of 1000 tips ) 1 units in each of 100 Municipal Hospitals ( Year 2011-12) | NS | 0.03 | Post Review | 31/Jul/11 | NA | 10/Aug/11 | 25/Aug/11 | 24/Sep/11 | NA | 4/Oct/11 | 3/Dec/11 |
| AG29N | Micropippette tips for taking samples reagents (1 Unit of 1000 tips ) 1 units in each of 100 Municipal Hospitals ( Year 2012-13) | NS | 0.03 | Post Review | 31/Jul/12 | NA | 10/Aug/12 | 25/Aug/12 | 24/Sep/12 | NA | 4/Oct/12 | 3/Dec/12 |
| AG29O | Urine protein sticks ( 1 Unit of 100 sticks) 2 Units per month for each of 100 Municipal Hospitals ( Year 2010-11) | NS | 0.96 | Post Review | 18/Feb/11 | NA | 28/Feb/11 | 15/Mar/11 | 14/Apr/11 | NA | 24/Apr/11 | 23/Jun/11 |
|  |  |  |  |  |  |  | This package quantity is already covered under Package AG29U. It may be dropped |
| AG29P | Urine protein sticks ( 1 Unit of 100 sticks) 2 Units per month for each of 100 Municipal Hospitals ( Year 2011-12) | NS | 0.96 | Post Review | 31/Jul/11 | NA | 10/Aug/11 | 25/Aug/11 | 24/Sep/11 | NA | 4/Oct/11 | 3/Dec/11 |
| AG29Q | Urine protein sticks ( 1 Unit of 100 sticks) 2 Units per month for each of 100 Municipal Hospitals ( Year 2012-13) | NS | 0.96 | Post Review | 31/Jul/12 | NA | 10/Aug/12 | 25/Aug/12 | 24/Sep/12 | NA | 4/Oct/12 | 3/Dec/12 |
| AG29R | ECG Paper 4 Units per month in each of 100 Municipal Hospitals (Year 2010 – 2011) | NS | 0.53 | Post Review | 18/Feb/11 | NA | 28/Feb/11 | 15/Mar/11 | 14/Apr/11 | NA | 24/Apr/11 | 23/Jun/11 |
|  |  |  |  |  |  |  | On Hold. Tender will be floated based on the requirement/usage of ECG paper rolls. |
| AG29S | ECG Paper 4 Units per month in each of 100 Municipal Hospitals (Year 2011 – 2012) | NS | 0.53 | Post Review | 31/Jul/11 | NA | 10/Aug/11 | 25/Aug/11 | 24/Sep/11 | NA | 4/Oct/11 | 3/Dec/11 |
| AG29T | ECG Paper 4 Units per month in each of 100 Municipal Hospitals (Year 2012 – 2013) | NS | 0.53 | Post Review | 31/Jul/12 | NA | 10/Aug/12 | 25/Aug/12 | 24/Sep/12 | NA | 4/Oct/12 | 3/Dec/12 |
| AG29U1 | Sr.Cholesterol Kit 150 ml with Standard (5726 Nos) | NCB | 4.58 | Post Review | 5/Nov/11 | NA | 15/Nov/11 | 15/Dec/11 | 29/Jan/12 | NA | 8/Feb/12 | 8/May/12 |
|  |  |  |  |  |  |  | 22/Nov/11 | 22/Dec/11 |  |  |  |  |
| AG29U2 | Sr.Creatinine Kit 240 ml with standard (1721 Nos) | NCB | 1.64 | Post Review | 5/Nov/11 | NA | 15/Nov/11 | 15/Dec/11 | 29/Jan/12 | NA | 8/Feb/12 | 8/May/12 |
|  |  |  |  |  |  |  | 22/Nov/11 | 22/Dec/11 |  |  |  |  |
| AG29U3 | Urine Albumin Sticks (one box of 100 sticks)(6087 Nos) | NCB | 1.42 | Post Review | 5/Nov/11 | NA | 15/Nov/11 | 15/Dec/11 | 29/Jan/12 | NA | 8/Feb/12 | 8/May/12 |
|  |  |  |  |  |  |  | 23/Nov/11 | 23/Dec/11 |  |  |  |  |
| AG29U4 | Glucose Kit 300 ml with standard (17297 NOs) | NCB | 13.56 | Post Review | 5/Nov/11 | NA | 15/Nov/11 | 15/Dec/11 | 29/Jan/12 | NA | 8/Feb/12 | 8/May/12 |
|  | Distilled Water of 5 litre can (17297 NOs) |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  | 23/Nov/11 | 23/Dec/11 |  |  |  |  |
| AG29V | Reagents and Consumables per annum for 1139 additional PHCs, 100 Municipal Hospitals, 400 block PHCs and GH for 270 GHs (Year 2011 – 2012) | ICB | 111.80 | Prior Review | 21/Jul/11 | 31/Jul/11 | 10/Aug/11 | 24/Sep/11 | 23/Nov/11 | 13/Dec/11 | 23/Dec/11 | 21/Apr/12 |
| AG29W | Reagents and Consumables per annum for 1139 additional PHCs, 100 Municipal Hospitals, 400 block PHCs and GH for 270 GHs (Year 2012 – 2013) | ICB | 111.80 | Prior Review | 21/Jul/12 | 31/Jul/12 | 10/Aug/12 | 24/Sep/12 | 23/Nov/12 | 13/Dec/12 | 23/Dec/12 | 22/Apr/13 |
| AG29X | Printing of Training Modules for CVD / DM for 270 Hospitals, 1539 PHCs and 100 Municipal Hospitals | NS | 1.26 | Post Review | 18/Feb/11 | NA | 28/Feb/11 | 15/Mar/11 | 14/Apr/11 | NA | 24/Apr/11 | 23/Jun/11 |
|  |  |  |  |  |  |  | 19/Aug/11 | 5/Sep/11 |  |  | 19/Sep/11 | 18/Nov/11 |
| AG29Y | Training Manual for CP / CRP | NS | 0.33 | Post Review | 18/Feb/11 | NA | 28/Feb/11 | 15/Mar/11 | 14/Apr/11 | NA | 24/Apr/11 | 23/Jun/11 |
|  |  |  |  |  |  |  | 19/Aug/11 | 5/Sep/11 |  |  | 19/Sep/11 | 18/Nov/11 |
| AG29Z | Printing of Screening Protocols for Hypertension and Diabetes | NS | 1.30 | Post Review | 18/Feb/11 | NA | 28/Feb/11 | 15/Mar/11 | 14/Apr/11 | NA | 24/Apr/11 | 23/Jun/11 |
| AG29AA | Printing of Treatment Protocols for Hypertension | NS | 1.30 | Post Review | 18/Feb/11 | NA | 28/Feb/11 | 15/Mar/11 | 14/Apr/11 | NA | 24/Apr/11 | 23/Jun/11 |
| AG29AB | Printing of Treatment Protocols for Diabetes | NS | 1.30 | Post Review | 18/Feb/11 | NA | 28/Feb/11 | 15/Mar/11 | 14/Apr/11 | NA | 24/Apr/11 | 23/Jun/11 |
|  | Cervical Cancer Screening Programme |  |  |  |  |  |  |  |  |  |  |  |
| AG30 | Manual Colposcope | NCB | 28.80 | Post Review | 9/Jun/10 | NA | 27/Dec/10 | 26/Jan/11 | 12/Mar/11 | NA | 22/Mar/11 | 20/Jun/11 |
|  |  |  |  |  |  |  | 28/Feb/11 | 30/Mar/11 | Technical and commercial evaluation completed. Placed before the Board. (To be retendered after Board approval). |
|  |  |  |  |  |  |  | 12/Oct/11 | 11/Nov/11 | Under Evaluation |
| AG31 | VIA/VILI KIT incl Magnavision Lamps to all screening centre | ICB | 81.64 | Prior Review | 30/May/10 | 6/Dec/10 | 8/Dec/10 | 28/Jan/11 | 29/Mar/11 | 18/Apr/11 | 28/Apr/11 | 26/Aug/11 |
|  |  |  |  |  |  |  | 08/Dec/10 | 29/Apr/11 | Schedule-I items are ordered on 19.10.11. Schedule-II is dropped. Schedule-III retendered as per NCB procedure and opening on 13/12/11 |
|  |  |  |  |  |  |  | 14/Nov/11 | 13/Dec/11 |  |
| AG32 | One Microscope Binocular for each medical college | NS | 0.98 | Post Review | 27/Oct/10 | NA | 27/Feb/11 | 14/Mar/11 | 13/Apr/11 | NA | 23/Apr/11 | 22/Jun/11 |
|  |  |  |  |  |  |  | 02/Aug/11 | 16/Aug/11 |  |  | 04/Nov/11 | 03/Jan/12 |
| AG33 | Colposcopy accessories kit contains Biopsy Forceps, Endo Cervical Currette & Endo Cervical Speculum | NCB | 2.88 | Post Review | 28/Aug/10 | NA | 27/Dec/10 | 26/Jan/11 | 12/Mar/11 | NA | 22/Mar/11 | 20/Jun/11 |
|  |  |  |  |  |  |  | 1/Mar/11 | 31/Mar/11 | L1 Bidder rate higher than market rate and also not qualify on end user certificate. |
|  |  |  |  |  |  |  | 17/Oct/11 | 16/Nov/11 |  |  |  |  |
| AG34a | Printing of Booklets, Manuals, Register & Forms, etc ( Year 2010-11) | NCB | 10.36 | Post Review | 28/Aug/10 | NA | 31/Jan/11 | 2/Mar/11 | 16/Apr/11 | NA | 26/Apr/11 | 25/Jul/11 |
|  |  |  |  |  |  |  | Bid Documents send to TNMSC on 02/12/11. |
| AG34b | Printing of Booklets, Manuals, Register & Forms, etc ( Year 2011-12) | NCB | 3.37 | Post Review | 28/Aug/10 | NA | 31/Jan/12 | 1/Mar/12 | 15/Apr/12 | NA | 25/Apr/12 | 24/Jul/12 |
| AG34c | Printing of Booklets, Manuals, Register & Forms, etc ( Year 2011-12) | NCB | 3.37 | Post Review | 28/Aug/10 | NA | 31/Jan/13 | 2/Mar/13 | 16/Apr/13 | NA | 26/Apr/13 | 25/Jul/13 |
|  | Cervical Cancer Screening Programme (NEW PACKAGES) |  |  |  |  |  |  |  |  |  |  |
| AG35a | Reagents ( Year 2010-11) | NCB | 2.96 | Post Review | 31/Dec/10 | NA | 10/Jan/11 | 9/Feb/11 | 26/Mar/11 | NA | 5/Apr/11 | 4/Jul/11 |
|  |  |  |  |  |  |  | 01/Mar/11 | 12/Apr/11 | None of the bidder qualified on end user certificate. Retendered with revised qualification criteria |
|  |  |  |  |  |  |  | 17/Oct/11 | 16/Nov/11 | Under evaluation |
| AG35b | Reagents ( Year 2011-12) | NCB | 5.48 | Post Review | 31/Dec/11 | NA | 10/Jan/12 | 9/Feb/12 | 25/Mar/12 | NA | 4/Apr/12 | 3/Jul/12 |
| AG35c | Reagents ( Year 2012-13) | NCB | 5.48 | Post Review | 31/Dec/12 | NA | 10/Jan/13 | 9/Feb/13 | 26/Mar/13 | NA | 5/Apr/13 | 4/Jul/13 |
| AG36a | Chemicals and Consumables ( Year 2010-11) | NCB | 1.68 | Post Review | 31/Dec/10 | NA | 10/Jan/11 | 9/Feb/11 | 26/Mar/11 | NA | 5/Apr/11 | 4/Jul/11 |
|  |  |  |  |  |  |  | 01/Mar/11 | 12/Apr/11 |  |  | 30/Aug/11 | 28/Nov/11 |
| AG36b | Chemicals and Consumables ( Year 2011-12) | NCB | 2.41 | Post Review | 31/Dec/11 | NA | 10/Jan/12 | 9/Feb/12 | 25/Mar/12 | NA | 4/Apr/12 | 3/Jul/12 |
| AG36c | Chemicals and Consumables ( Year 2012-13) | NCB | 2.41 | Post Review | 31/Dec/12 | NA | 10/Jan/13 | 9/Feb/13 | 26/Mar/13 | NA | 5/Apr/13 | 4/Jul/13 |
| AG30a | Cryotherapy Unit | NCB | 7.33 | Post Review | 17/Dec/10 | NA | 27/Dec/10 | 26/Jan/11 | 12/Mar/11 | NA | 22/Mar/11 | 20/Jun/11 |
|  |  |  |  |  |  |  | 1/Mar/11 | 31/Mar/11 |  |  | 14/Oct/11 | 12/Jan/12 |
| AG34d | Printing of VIA / VILI Modules | NS | 1.04 | Post Review | 5/Feb/11 | NA | 15/Feb/11 | 2/Mar/11 | 1/Apr/11 | NA | 11/Apr/11 | 10/Jun/11 |
|  |  |  |  |  |  |  | 19/Aug/11 | 5/Sep/11 | Orders Placed to L1 bidder on 19/9/11. Not willing to supply |
|  |  |  |  |  |  |  | 8/Oct/11 | 24/Oct/11 |  |  | 31/Oct/11 | 30/Dec/11 |
| AG34e | Printing of Colposcopy / Cryotherapy Modules | NS | 0.08 | Post Review | 5/Feb/11 | NA | 15/Feb/11 | 2/Mar/11 | 1/Apr/11 | NA | 11/Apr/11 | 10/Jun/11 |
|  |  |  |  |  |  |  | 19/Aug/11 | 5/Sep/11 |  |  | 19/Sep/11 | 18/Nov/11 |
| AG34f | Printing of Mammography Modules for Radiologists & USG guided Biopsy Modules | NS | 0.02 | Post Review | 5/Feb/11 | NA | 15/Feb/11 | 2/Mar/11 | 1/Apr/11 | NA | 11/Apr/11 | 10/Jun/11 |
|  |  |  |  |  |  |  | Activity on hold owing to availing mammography services thro CMHIS Hospitals |
| AG34g | Training Manual for CP / CRP | NS | 0.33 | Post Review | 5/Feb/11 | NA | 15/Feb/11 | 2/Mar/11 | 1/Apr/11 | NA | 11/Apr/11 | 10/Jun/11 |
|  |  |  |  |  |  |  | 19/Aug/11 | 5/Sep/11 |  |  | 19/Sep/11 | 18/Nov/11 |
| AG34h | Printing of Protocols for Cervical Cancer | NS | 1.30 | Post Review | 21/Jan/11 | NA | 31/Jan/11 | 15/Feb/11 | 17/Mar/11 | NA | 27/Mar/11 | 26/May/11 |
| AG34i | Printing of Protocols for Breast Cancer | NS | 1.30 | Post Review | 21/Jan/11 | NA | 31/Jan/11 | 15/Feb/11 | 17/Mar/11 | NA | 27/Mar/11 | 26/May/11 |
| AG34j | Printing of Sensitization Modules | NS | 0.63 | Post Review | 5/Feb/11 | NA | 15/Feb/11 | 2/Mar/11 | 1/Apr/11 | NA | 11/Apr/11 | 10/Jun/11 |
|  |  |  |  |  |  |  | 19/Aug/11 | 5/Sep/11 | Orders Placed to L1 bidder on 19/9/11. Not willing to supply |
|  |  |  |  |  |  |  | 8/Oct/11 | 24/Oct/11 |  |  | 31/Oct/11 | 30/Dec/11 |
| AG37 | Mammography Units | ICB | 64.00 | Prior Review | 30/May/10 | 9/Jun/10 | 27/Mar/11 | 11/May/11 | 10/Jul/11 | 30/Jul/11 | 9/Aug/11 | 7/Dec/11 |
|  |  |  |  |  |  |  | Activity on hold owing to availing mammography services thro CMHIS Hospitals |
|  | IEC Activities |  |  |  |  |  |  |  |  |  |  |  |
| AG55 | Information Boards in public places | NS | 3.84 | Post Review | 21/Nov/10 | NA | 1/Dec/10 | 16/Dec/10 | 15/Jan/11 | NA | 25/Jan/11 | 26/Mar/11 |
|  |  |  |  |  |  |  | 1/Oct/10 | 21/Oct/10 |  |  | 16/Nov/10 |  |
| AG57A | Printing of Calendars, Diaries ( Year 2010-11) | NS | 0.20 | Post Review | 21/Nov/10 | NA | 1/Dec/10 | 16/Dec/10 | 15/Jan/11 | NA | 25/Jan/11 | 26/Mar/11 |
|  |  |  |  |  |  |  | 2/Oct/10 | 9/Nov/10 |  |  | 1/Dec/10 | 10/03/11 |
|  | HMS & HMIS Thro Elcot |  |  |  |  |  |  |  |  |  |  |  |
| Phase II | Computers with Peripherals |  |  |  |  |  |  |  |  |  |  |  |
| AG58-67--P2H1+ AG58-67—P2H2 | Computers + Dot Matrix Printers For HMS in Phase II hospitals | ICB | 158.50 | Prior Review | 16/Dec/10 | 26/Dec/10 | 5/Jan/11 | 19/Feb/11 | 20/Apr/11 | 10/May/11 | 20/May/11 | 17/Sep/11 |
| AG58-67—P2H3 | Online UPS for 222 hospitals + 26 JDHS offices including electrical cabling 5 KVA- 44 numbers 7.5 KVA-86 numbers 10 KVA-42 numbers 15 KVA-50 numbers 20 KVA- 16 numbers Wiring additional battery cost 4th and 5th year | ICB | 129.86 | Prior Review | 16/Dec/10 | 26/Dec/10 | 5/Jan/11 | 19/Feb/11 | 20/Apr/11 | 10/May/11 | 20/May/11 | 17/Sep/11 |
| AG58-67—P2H4 | Computer Furnitures | NCB | 38.50 | Post Review | 26/Dec/10 | NA | 5/Jan/11 | 4/Feb/11 | 21/Mar/11 | NA | 31/Mar/11 | 29/Jun/11 |
| AG58-67—P2H5 | Server for Phase II hospitals | ICB | 35.00 | Prior Review | 16/Dec/10 | 26/Dec/10 | 5/Jan/11 | 19/Feb/11 | 20/Apr/11 | 10/May/11 | 20/May/11 | 17/Sep/11 |
| AG58-67--P2H6 | Hosting charges payable to ELCOT for hosting the servers at their data center | Direct Contracting | 21.45 | Post Review | 26/Dec/10 | NA | 5/Jan/11 | 20/Jan/11 | 19/Feb/11 | NA | 1/Mar/11 | 30/Apr/11 |
| AG58-67—P2H7 | TNSWAN Connectivity for 222 locations for a period of 5 years | Direct Contracting | 85.00 | Post Review | 26/Dec/10 | NA | 5/Jan/11 | 20/Jan/11 | 19/Feb/11 | NA | 1/Mar/11 | 30/Apr/11 |
| AG58-67—P2H8 | Broadband connectivity for 222 hospitals + 15 PHC's | Direct Contracting | 5.97 | Post Review | 26/Dec/10 | NA | 5/Jan/11 | 20/Jan/11 | 19/Feb/11 | NA | 1/Mar/11 | 30/Apr/11 |
| AG58-67—P2H14 | Redundant BB VPN 8 MBPS connectivity at the server end | Direct Contracting | 6.00 | Post Review | 26/Dec/10 | NA | 5/Jan/11 | 20/Jan/11 | 19/Feb/11 | NA | 1/Mar/11 | 30/Apr/11 |
|  | LAN Connectivity |  |  |  |  |  |  |  |  |  |  |  |
| AG58-67—P2H13 | LAN Connectivity in 222 hospitals + 15 PHC's | NCB | 37.50 | Post Review | 26/Dec/10 | NA | 5/Jan/11 | 4/Feb/11 | 21/Mar/11 | NA | 31/Mar/11 | 29/Jun/11 |
|  | Consumables |  |  |  |  |  |  |  |  |  |  |  |
| AG58-67—P2H9 | Pre Printed Stationery | ICB | 81.32 | Prior Review | 16/Dec/10 | 26/Dec/10 | 5/Jan/11 | 19/Feb/11 | 20/Apr/11 | 10/May/11 | 20/May/11 | 17/Sep/11 |
|  | Pre printed -OP Slip |  |  |  |  |  |  |  |  |  |  |  |
|  | Pre Printed- OP case Records |  |  |  |  |  |  |  |  |  |  |  |
|  | Pre Printed -Lab reports |  |  |  |  |  |  |  |  |  |  |  |
| AG58-67—P2H10 | A4 Papers | NCB | 20.00 | Post Review | 26/Dec/10 | NA | 5/Jan/11 | 4/Feb/11 | 21/Mar/11 | NA | 31/Mar/11 | 29/Jun/11 |
| AG58-67—P2H11 | Cartridges | NCB | 3.00 | Post Review | 26/Dec/10 | NA | 5/Jan/11 | 4/Feb/11 | 21/Mar/11 | NA | 31/Mar/11 | 29/Jun/11 |
| AG58-67—P2H12 | Ink Bank | NCB | 3.00 | Post Review | 26/Dec/10 | NA | 5/Jan/11 | 4/Feb/11 | 21/Mar/11 | NA | 31/Mar/11 | 29/Jun/11 |
|  | HMIS for Municipal Hospitals |  |  |  |  |  |  |  |  |  |  |  |
| AG58-67—P2H15 | Desktop Computer for Municipal Hospitals | NCB | 2.80 | Post Review | 31/Dec/10 | NA | 10/Jan/11 | 9/Feb/11 | 26/Mar/11 | NA | 5/Apr/11 | 4/Jul/11 |
| AG58-67—P2H16 | Furniture Set for Municipal Hospitals | NS | 0.70 | Post Review | 31/Dec/10 | NA | 10/Jan/11 | 25/Jan/11 | 24/Feb/11 | NA | 6/Mar/11 | 5/May/11 |
| AG58-67—P2H17 | UPS for Municipal Hospitals | NS | 0.40 | Post Review | 31/Dec/10 | NA | 10/Jan/11 | 25/Jan/11 | 24/Feb/11 | NA | 6/Mar/11 | 5/May/11 |
| AG58-67—P2H18 | Broad Band Connectivity for Municipal Hospitals (2011-2013) | NCB | 3.80 | Post Review | 31/Dec/10 | NA | 10/Jan/11 | 9/Feb/11 | 26/Mar/11 | NA | 5/Apr/11 | 4/Jul/11 |
| AG58-67—P2H19 | Service Chareges 2.5 % for ELCOT | Direct Contracting | 0.20 | Post Review | 31/Dec/10 | NA | 10/Jan/11 | 25/Jan/11 | 24/Feb/11 | NA | 6/Mar/11 | 5/May/11 |
| HMIS Phase III Computers with Peripherals |  |  |  |  |  |  |  |  |  |  |  |
| AG68-P3H1 | Computers For HMS in Phase III hospitals | ICB | 42.936 | Prior Review | 1-Jan-11 | 5-Jan-11 | 10-Jan-11 | 25-Feb-11 | 10-Mar-11 | 20-Mar-11 | 5-Apr-11 | 10-Aug-11 |
| AG68-P3H2 | 80 column Dot Matrix Printers | NS |  | Post Review | 1-Jan-11 | 5-Jan-11 | 10-Jan-11 | 25-Feb-11 | 10-Mar-11 | 20-Mar-11 | 5-Apr-11 | 10-Aug-11 |
| AG68-P3H3 | Online UPS for 29 DME Institutions including electrical cabling | ICB |  | Prior Review | 1-Jan-11 | 5-Jan-11 | 10-Jan-11 | 25-Feb-11 | 10-Mar-11 | 20-Mar-11 | 5-Apr-11 | 10-Aug-11 |
| AG68-P3H4 | Computer Furnitures | NCB |  | Post Review | 1-Jan-11 | 5-Jan-11 | 10-Jan-11 | 10-Feb-11 | NA | NA | 25-Mar-11 | 30-Jul-11 |
| AG68-P3H5 | Server for Phase III hospitals | ICB |  | Prior Review | 1-Jan-11 | 5-Jan-11 | 10-Jan-11 | 25-Feb-11 | 10-Mar-11 | 20-Mar-11 | 5-Apr-11 | 10-Aug-11 |
| AG68-P3H6 | Hosting charges payable to ELCOT for hosting the servers at their data center | Direct Contracting |  | Post Review | 1-Jan-11 | 5-Jan-11 | 10-Jan-11 | 25-Feb-11 | 10-Mar-11 | 20-Mar-11 | 5-Apr-11 | 10-Aug-11 |
| AG68-P3H7 | TNSWAN Connectivity for all DME Institutions for a period of 3 years- Hardware and last mile connectivity | Direct Contracting |  | Post Review | 1-Jan-11 | 5-Jan-11 | 10-Jan-11 | 25-Feb-11 | 10-Mar-11 | 20-Mar-11 | 5-Apr-11 | 10-Aug-11 |
| AG68-P3H8 | Redundant Broadband VPN connectivity for all DME Institutions for a period of 3 years | Direct Contracting |  | Post Review | 1-Jan-11 | 5-Jan-11 | 10-Jan-11 | 25-Feb-11 | 10-Mar-11 | 20-Mar-11 | 5-Apr-11 | 10-Aug-11 |
| AG68-P3H9 | LAN Connectivity for Group I DME hospitals | NCB |  | Post Review | 1-Jan-11 | 5-Jan-11 | 10-Jan-11 | 10-Feb-11 | NA | NA | 25-Mar-11 | 30-Jul-11 |
| AG68-P3H10 | LAN Connectivity for Group II DME hospitals | NCB |  | Post Review | 1-Jan-11 | 5-Jan-11 | 10-Jan-11 | 10-Feb-11 | NA | NA | 25-Mar-11 | 30-Jul-11 |
|  | Consumables |  |  |  |  |  |  |  |  |  |  |  |
| AG68-P3H11 | Pre Printed Stationery | NCB |  | Post Review | 1-Jan-11 | 5-Jan-11 | 10-Jan-11 | 10-Feb-11 | NA | NA | 25-Mar-11 | 30-Jul-11 |
| AG68-P3H12 | A4 Papers | NCB |  | Post Review | 1-Jan-11 | 5-Jan-11 | 10-Jan-11 | 10-Feb-11 | NA | NA | 25-Mar-11 | 30-Jul-11 |
| AG68-P3H13 | Cartridges (4 numbers needed per year per printer * 4300 DMP's * 3years) | NS |  | Post Review | 1-Jan-11 | 5-Jan-11 | 10-Jan-11 | 10-Feb-11 | NA | NA | 25-Mar-11 | 30-Jul-11 |
| AG68-P3H14 | Ink Bank (12 numbers needed per year per printer * 4300 DMP's * 3years) | NCB |  | Post Review | 1-Jan-11 | 5-Jan-11 | 10-Jan-11 | 10-Feb-11 | NA | NA | 25-Mar-11 | 30-Jul-11 |
| AG68-P3H15 | Server Hardware for State Health Data Resource Centre | NCB |  | Post Review | 1-Jan-11 | 5-Jan-11 | 10-Jan-11 | 10-Feb-11 | NA | NA | 25-Mar-11 | 30-Jul-11 |
|  | CEmONC Services |  |  |  |  |  |  |  |  |  |  |  |
| AG69 | Equipments for maternity wings at 8 medical college hospitals | ICB | 80.00 | Prior Review | 16/Dec/10 | 26/Dec/10 | 27/May/11 | 11/Jul/11 | 9/Sep/11 | 29/Sep/11 | 9/Oct/11 | 6/Feb/12 |
|  |  |  |  |  |  |  | Specification and Requirement under preparation |
|  | Rationalisation of Lab Services |  |  |  |  |  |  |  |  |  |  |  |
| AG70 | One major laboratory with all facilities in each district – Goods | ICB | 96.00 | Prior Review | 16/Dec/10 | 26/Dec/10 | 27/May/11 | 11/Jul/11 | 9/Sep/11 | 29/Sep/11 | 9/Oct/11 | 6/Feb/12 |
|  |  |  |  |  |  |  | Activity on hold |
| AG71a | Furnitures and cubicles to the new office at 3rd floor of TNMSC Head Office | NCB | 30.00 | Post Review | 26/Dec/10 | NA | 5/Jan/11 | 4/Feb/11 | 21/Mar/11 | NA | 31/Mar/11 | 29/Jun/11 |
| AG71b | Electrical Work at 3rd Floor of TNMSC Ltd. | NS |  | Post Review | 26/Dec/10 | NA | 5/Jan/11 | 20/Jan/11 | 19/Feb/11 | NA | 1/Mar/11 | 30/Apr/11 |
| AG71c | Air Conditioner to 3rd Floor of TNMSC Ltd., | NCB |  | Post Review | 26/Dec/10 | NA | 5/Jan/11 | 4/Feb/11 | 21/Mar/11 | NA | 31/Mar/11 | 29/Jun/11 |
| AG71d | 160 KVA diesel Generator with accessories | NS |  | Post Review | 26/Dec/10 | NA | 5/Jan/11 | 20/Jan/11 | 19/Feb/11 | NA | 1/Mar/11 | 30/Apr/11 |
| AG71e | Fire Alarm System | NS |  | Post Review | 26/Dec/10 | NA | 5/Jan/11 | 20/Jan/11 | 19/Feb/11 | NA | 1/Mar/11 | 30/Apr/11 |
| AG71f | Servers and Other Hardwares | NCB |  | Post Review | 26/Dec/10 | NA | 5/Jan/11 | 4/Feb/11 | 21/Mar/11 | NA | 31/Mar/11 | 29/Jun/11 |
| AG71g | Computers / Workmate | NCB |  | Post Review | 26/Dec/10 | NA | 5/Jan/11 | 4/Feb/11 | 21/Mar/11 | NA | 31/Mar/11 | 29/Jun/11 |
| AG71h | Heavy Duty Printers | NS |  | Post Review | 26/Dec/10 | NA | 5/Jan/11 | 20/Jan/11 | 19/Feb/11 | NA | 1/Mar/11 | 30/Apr/11 |
| AG71k | Laptop Computers | NS |  | Post Review | 26/Dec/10 | NA | 5/Jan/11 | 20/Jan/11 | 19/Feb/11 | NA | 1/Mar/11 | 30/Apr/11 |
| AG71l | LAN Cabling and Telephone Extension | NS |  | Post Review | 26/Dec/10 | NA | 5/Jan/11 | 20/Jan/11 | 19/Feb/11 | NA | 1/Mar/11 | 30/Apr/11 |
|  |  |  |  |  |  |  | For (AG71a-l) detailed proposals for preparing the consultancy package is to be prepared |
| AG72 | Equipments for Additional 2 Floors | NCB | 10.00 | Post Review | 26/Dec/10 | NA | 27/May/11 | 26/Jun/11 | 10/Aug/11 | NA | 20/Aug/11 | 18/Nov/11 |
|  |  |  |  |  |  |  | Specification and Requirement under preparation |
|  | Poison Treatment Centres |  |  |  |  |  |  |  |  |  |  |  |
| AG73a | Ventilator Adult | NCB | 16.00 | Post Review | 6/Sep/10 | NA | 9/Sep/10 | 19/Oct/10 | 3/Dec/10 | NA | 13/Dec/10 | 13/Mar/11 |
|  |  |  |  |  |  |  | 9/Sep/10 | 19/Oct/10 |  |  | 25/Apr/11 | 24/Jul/11 |
| AG73b | Defibrilator | NCB | 5.41 | Post Review | 6/Sep/10 | NA | 16/Sep/10 | 16/Oct/10 | 30/Nov/10 | NA | 10/Dec/10 | 10/Mar/11 |
|  | ECG Machine |  |  |  |  |  | 9/Sep/10 | 19/Oct/10 | 3/Dec/10 | NA | 13/Dec/10 | 13/Mar/11 |
|  | Cardiac Monitor |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  | 9/Sep/10 | 19/Oct/10 |  |  | 26/Apr/11 | 25/Jul/11 |
| AG73c | ICU Cot | NCB | 3.22 | Post Review | 6/Sep/10 | NA | 16/Sep/10 | 16/Oct/10 | 30/Nov/10 | NA | 10/Dec/10 | 10/Mar/11 |
|  | Mattresses for ICU cots |  |  |  |  |  |  |  |  |  |  |  |
|  | Saline Stand |  |  |  |  |  |  |  |  |  |  |  |
|  | Medicine trolley |  |  |  |  |  |  |  |  |  |  |  |
|  | Emergency crash cart/Drug trolley |  |  |  |  |  |  |  |  |  |  |  |
|  | Stretcher(SS complete) |  |  |  |  |  |  |  |  |  |  |  |
|  | Wheel chair(SS complete) |  |  |  |  |  | 9/Sep/10 | 20/Oct/10 | 4/Dec/10 | NA | 14/Dec/10 | 14/Mar/11 |
|  |  |  |  |  |  |  | 18/Apr/11 | 18/May/11 |  |  | 23/Sep/11 | 22/Dec/11 |
| AG73d | Pulse Oximeter | NCB | 4.48 | Post Review | 6/Sep/10 | NA | 9/Sep/10 | 20/Oct/10 | 4/Dec/10 | NA | 14/Dec/10 | 14/Mar/11 |
|  |  |  |  |  |  |  | 9/Sep/10 | 20/Oct/10 |  |  | 1/Mar/11 | 30/May/11 |
| AG73e | Suction apparatus | NS | 0.94 | Post Review | 6/Sep/10 | NA | 16/Sep/10 | 1/Oct/10 | 31/Oct/10 | NA | 10/Nov/10 | 9/Jan/11 |
|  | Nebuliser |  |  |  |  |  |  |  |  |  |  |  |
|  | BP Apparatus |  |  |  |  |  |  |  |  |  |  |  |
|  | Stethoscope |  |  |  |  |  |  |  |  |  |  |  |
|  | Resuscitation kit-Adult and Pediatric |  |  |  |  |  | 9/Sep/10 | 27/Sep/10 | 27/Oct/10 | NA | 6/Nov/10 | 5/Jan/11 |
|  |  |  |  |  |  |  | 2/Aug/11 | 16/Aug/11 |  |  | 22/Sep/11 | 21/Nov/11 |
| AG73f | Chairs and Tables for Doctors, Nurses, Visitors | NS | 0.48 | Post Review | 6/Sep/10 | NA | 16/Sep/10 | 1/Oct/10 | 31/Oct/10 | NA | 10/Nov/10 | 9/Jan/11 |
|  | Wooden Stool |  |  |  |  |  | 9/Sep/10 | 21/Oct/10 | 20/Nov/10 | NA | 30/Nov/10 | 29/Jan/11 |
|  |  |  |  |  |  |  | 9/Sep/10 | 21/Oct/10 |  |  | 23/Aug/11 | 22/Oct/11 |
| AG73g | Computer with Accessories and Furnitures (Table & Chair) | NS | 1.12 | Post Review | 6/Sep/10 | NA | 9/Sep/10 | 21/Oct/10 | 20/Nov/10 | NA | 30/Nov/10 | 29/Jan/11 |
|  |  |  |  |  |  |  | 9/Sep/10 | 21/Oct/10 | Dropped |
| AG73h | Oxygen Cylinder | NS | 0.35 | Post Review | 6/Sep/10 | NA | 9/Sep/10 | 27/Sep/10 | 27/Oct/10 | NA | 6/Nov/10 | 5/Jan/11 |
|  |  |  |  |  |  |  | 9/Sep/10 | 27/Sep/10 |  |  | 7/Apr/11 | 6/Jun/11 |
| AG73i | Inverter | NS | 0.38 | Post Review | 30/Dec/10 | NA | 9/Jan/11 | 24/Jan/11 | 23/Feb/11 | NA | 5/Mar/11 | 4/May/11 |
|  |  |  |  |  |  |  | Dropped |
| AG73j | Centralized Oxygen Supply System in 38 GHs | ICB | 28.50 | Post Review | 6/Jan/10 | NA | 16/Jan/10 | 31/Jan/10 | 2/Mar/10 | NA | 12/Mar/10 | 11/May/10 |
|  |  |  |  |  |  |  | Amendment proposal to be put up for SEC for additional fund. |
| AG74 | Vehicle for DPMUs (Coimbatore, Ariyalur and Chennai) | DGS&D | 2.10 | Post Review | 10/Jan/11 | NA | 20/Jan/11 | 4/Feb/11 | 6/Mar/11 | NA | 16/Mar/11 | 30/Mar/11 |
|  |  |  |  |  |  |  |  |  |  |  | 31/Oct/11 | 30/Nov/11 |
| AG75 | Software for Radiology information systems | NS | 1.35 | Post Review | 10/Jan/11 | NA | 20/Jan/11 | 4/Feb/11 | 6/Mar/11 | NA | 16/Mar/11 | 30/Mar/11 |
|  |  |  |  |  |  |  | Tender to be floated after finalizing DR Tender |
| AG76 | Supply of HEPA FILTERS for 10 Hospitals (A/C System) | NCB | 10.00 | Post Review | 22/Aug/11 | NA | 1/Sep/11 | 1/Oct/11 | 1/Nov/11 | NA | 10/Nov/11 | 10/Feb/11 |
|  |  |  |  |  |  |  | 12/Oct/11 | 11/Nov/11 | Under evaluation |
|  |  |  | 2289.89 |  |  |  |  |  |  |  |  |  |

Annex 3:  Procurement Schedule for Non-Consultancy Services

| Package No. | Description | Method of Procurement | Estimated Cost (Million Rs.) | Prior or Post Review | Submission of Draft Bid Document to the Bank | No objection for Bid documents by the World Bank | Publication of IFB in Newspapers and UNDB/ dgMarket and beginning of sale of bid document | Receipt and opening of Bids | Submission of BER to Bank for No Objection | Receipt of No Objection of Bank for BER | Signing of the contract | Contract Completed |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| AS12 | Outsourcing of housekeeping services (laundry, cleaning, security, food) at 32 HQ & Other Major hospitals ( Year 2011-12) | ICB | 192 | Prior Review | 9/Feb/10 | 19/Feb/10 | 1/Mar/11 | 15/Apr/11 | 14/Jun/11 | 4/Jul/11 | 14/Jul/11 | 11/Nov/11 |
| AS13 | Outsourcing of housekeeping services (laundry, cleaning, security, food) at 32 HQ & Other Major hospitals ( Year 2012-13) | ICB | 192 | Prior Review | 9/Feb/10 | 19/Feb/10 | 1/Mar/12 | 15/Apr/12 | 14/Jun/12 | 4/Jul/12 | 14/Jul/12 | 11/Nov/12 |
| AS18 | Maintenance of DMS Annex and campus (through PPP) | NCB | 5.4 | Post Review | 19/Feb/10 | NA | 1/Mar/11 | 31/Mar/11 | 15/May/11 | NA | 25/May/11 | 23/Aug/11 |
|  | TOTAL (INR) Million |  | 389.40 |  |  |  |  |  |  |  |  |  |
|  | TOTAL (US$ M) (@INR 48/US$) |  | 8.1125 |  |  |  |  |  |  |  |  |  |
| Annex 3 A : Procurement Schedule for Non-Consultancy Services from 01.08.10 |
| This procurement package AS19 has been included in this procurement plan vide email dated 06.08.10 from World Bank. |
| AS19 | Production of edited, designed and printing the proposed books on 3 pilots | NS | 1.2 | Post Review | E-5 17/Aug/10 | NA | ** 20/ Aug/ 10 | 05/Sep/10 | NA | NA | 10/Sep/10 | 07/Jan/11 |
|  | New Packages |  |  |  |  |  |  |  |  |  |  |  |
| AS20 | Quality Check for labs once in 3 months for 3 years for Cancer Cervix and Breast Cancer Programme | NCB | 5.8 | Post Review | 17/May/11 | NA | 20-May-11 | 20-Jun-11 | 20-Jul-11 | 1-Aug-11 | 10-Aug-11 |  |
|  |  |  |  |  |  |  | Methodology to be arrived by PMU |
| AS21 | Quality Check for labs once in 3 months for 3 years for CVD and Diabetes Prevention Programme | NCB | 5.8 | Post Review | 17/May/11 | NA |  | 20-Jun-11 | 20-Jul-11 | 1-Aug-11 | 10-Aug-11 |  |
|  |  |  |  |  |  |  | Methodology to be arrived by PMU |
|  |  |  | 12.80 |  |  |  |  |  |  |  |  |  |

Annex 4:  Procurement Schedule for Consultancy Services

| Package No. | Description | Status | Method of Selection | Estimated Cost (Million Rs.) | Prior or Post Review | TOR, EOI notice drafted | Publication of EOI notice in UNDB and Newspapers | No Objection of Bank for Shortlist and RFP document | Issue RFP to short listed consultants | Receipt of proposals and opening technical proposals | Evaluation of technical proposals | Bank's No Objection to technical evaluation report | Opening of financial proposals, financial evaluation & finalize draft contract | Bank's no objection to draft contract | Contract Signed | Contract Completion |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| CS- 7/ PPP 3 | Hiring of 10 NGO consultants (Extension of existing contracts) 1* amended - savings = 4 | Proposed | Selection of Individual Consultants | 9 | Post Review | 30.11.10 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | 20.12.10 | 31.03.13 |
|  |  |  |  | 5 |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Current Status | Extension of the existing contract | 5 |  | 10.03.11 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | 30.05.11 | On going |
| CS -8 / PPP 4 | External agency to monitor PPPs and IEC 2* | Proposed | QCBS | 11.8 | Prior Review | 10.01.11 | 02.02.11 | 31.03.11 | 07.04.11 | 12.05.11 | 25.05.11 | 31.05.11 | 07.06.11 | 15.06.11 | 30.06.11 | 31.03.13 |
|  |  | Current Status |  |  |  | 01.01.12 | 21.01.12 | 04.03.12 | 06.03.12 | 06.04.12 | 13.04.12 | 22.04.12 | 27.04.12 | 12.05.12 | 20.05.12 | 31.03.13 |
| CS-9 / PPP 5 | Hiring an external agency to monitor the housekeeping services ( NGO monitoring ) 3* | Proposed | QCBS | 11.8 | Prior Review | 04.11.11 | 18.11.11 | 10.12.11 | 15.12.11 | 15.01.12 | 22.01.12 | 29.01.12 | 05.02.12 | 13.02.12 | 18.02.12 | 31.03.13 |
|  |  | Current Status |  |  |  | 01.01.12 | 21.01.12 | 04.03.12 | 06.03.12 | 06.04.12 | 13.04.12 | 22.04.12 | 27.04.12 | 12.05.12 | 20.05.12 | 31.03.13 |
| CS-10 / TDP 3 | Consultancy for conducting final evaluation of Tribal and CEmONC activities in the State ( AF ) 4* | Proposed | QCBS | 4.9 | Post Review | 07.11.11 | 21.11.11 | 13.12.11 | 18.12.11 | 18.01.12 | 25.01.12 | 01.02.12 | 08.02.12 | 16.02.12 | 21.02.12 | 24.02.13 |
|  |  | Current Status |  |  |  | 12.05.12 | 02.06.12 | 16.07.12 | 18.07.12 | 18.08.12 | 25.08.12 | 03.09.12 | 08.09.12 | 22.09.12 | 30.09.12 |  |
| CS-11 / HMIS 5 | Consultancy for development and implementation of HMS software for Medical Colleges (TCS) 5 * | Proposed | SSS (Extension of existing contract ) | 20 | Prior Review | 20.01.11 | N.A. | N.A. | 20.02.11 | 25.02.11 | 10.03.11 | N.A. | 24.03.11 | 02.04.11 | 17.04.11 | 31.03.13 |
|  |  | Current Status | SSS | 49.5 |  | 16.05.11 | N.A. | N.A. | 21.05.11 | 30.05.11 | 06.06.11 | N.A. | 07.07.11 | 07.07.11 | 07.07.11 | On going |
| CS-12 / HMIS 6 | Hiring an external agency for providing the services of IT Coordinators in all districts for HMIS/HMS implementation (ELCOT) 6* | Proposed | SSS (Extension of existing contract ) | 23.04 | Prior Review | 25.01.11 | N.A. | N.A. | 25.02.11 | 02.03.11 | 15.03.11 | N.A. | 20.03.11 | 07.04.11 | 22.04.11 | 31.03.13 |
|  |  | Current Status |  |  |  | 04.03.10 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | 10.03.10 | 10.03.10 | On going |
| CS – 13a / ICWM 1 | Hiring the services of the consultant firm contracted by APAC-VHS for retraining the health care providers: (SSS justification to be sent to WB) | Proposed | SSS may be deferred… | 8 | Prior Review | 15.03.11 | 08.04.11 | 11.05.11 | 18.05.11 | 23.06.11 | 06.07.11 | 13.07.11 | 20.07.11 | 28.07.11 | 12.08.11 |  |
|  |  | Current Status |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| CS-13 b / ICWM 2 | Consultant for assessing the Impact Evaluation of training on Infection Control and Waste Management 7 * | Proposed | CQS | 2.8 | Post Review | 16.11.11 | 23.11.11 | N.A. | 23.12.11 | 22.01.12 | 07.02.12 | N.A. | 07.02.12 | N.A. | 22.02.12 | 28.02.13 |
|  |  | Current Status |  |  |  | 12.05.12 | 02.06.12 | 16.07.12 | 18.07.12 | 18.08.12 | 25.08.12 | 03.09.12 | 08.09.12 | 22.09.12 | 30.09.12 |  |
| CS-14 / NCD 5 | Hiring the services of an agency for documentation of NCD up scaling activities in the state | Proposed | QCBS | 6 | Prior Review | 19.11.11 | 12.12.11 | 07.02.12 | 14.02.12 | 19.03.12 | 31.03.12 | 06.04.12 | 13.4.12 | 21.04.12 | 06.05.12 | 31.03.13 |
|  |  | Current Status |  |  |  | 01.12.11 | 21.12.11 | 04.02.12 | 06.02.12 | 06.03.12 | 13.03.12 | 22.03.12 | 27.03.12 | 12.04.12 | 20.05.12 |  |
| CS-15 / NCD 6 | Hiring the services of NIE for concurrent evaluation of the NCD programs (SSS justification to be sent to WB) | Proposed | SSS | 30.6 | Prior Review | 10.01.11 | 02.02.11 | 31.03.11 | 07.04.11 | 12.05.11 | 25.05.11 | 31.05.11 | 07.06.11 | 15.06.11 | 30.06.11 | 31.03.13 |
|  |  | Current Status |  |  |  | 04.06.11 | NA | NA | 08.06.11 | 22.06.11 | 23.06.11 | NA | NA | 08.07.11 | 08.07.11 | On going |
| CS-16 / NCD 7 | Hiring an external agency to monitor the NCD activities in up-scaling districts 8* | Proposed | QCBS | 12.1 | Prior Review | 22.11.11 | 29.11.11 | 27.12.11 | 03.01.12 | 08.01.12 | 21.01.12 | 26.01.12 | 02.02.12 | 10.02.12 | 23.02.12 | 31.03.13 |
|  |  | Current Status |  |  |  | 01.12.11 | 21.12.11 | 04.02.12 | 06.02.12 | 06.03.12 | 13.03.12 | 22.03.12 | 27.03.12 | 12.04.12 | 20.05.12 |  |
| CS-17 / NCD 8 | Consultant for End line Evaluation of NCD Components 9* | Proposed | QCBS | 10.3 | Prior Review | 25.11.11 | 02.12.11 | 29.01.12 | 05.02.12 | 10.02.12 | 23.02.12 | 29.02.12 | 07.03.12 | 15.03.12 | 30.03.12 | 31.03.13 |
|  |  | Current Status |  |  |  | 12.05.12 | 02.06.12 | 16.07.12 | 18.07.12 | 18.08.12 | 25.08.12 | 03.09.12 | 08.09.12 | 22.09.12 | 30.09.12 |  |
| CS - 18 / IA3 | Contracting Internal Auditors to audit the finance management of the project for 2011-13 10* | Proposed | LCS | 3 | Post Review | 25.03.11 | 4.1.11 | N.A. | 01.05.11 | 01.06.11 | 01.06.11 | N.A. | 15.06.11 | N.A. | 30.06.11 | 09.-9.11 |
|  |  | Current Status |  |  |  |  |  | NA | 01.11.11 | 29.11.11 | 02.12.11 | NA | 08.12.11 | NA | 11.12.11 |  |
| CS - 19 / HMIS 7 | Hiring the services of a Procurement Agent for procurement of hardware for HMIS (ELCOT) 11* | Proposed | SSS | 15.2 | Prior Review | done | N.A. | N.A. | done | done | done | N.A. | done | done | 10.03.10 |  |
|  |  | Current Status |  |  |  |  |  |  |  |  |  |  |  |  |  | On going |
| CS – 20 / PPA 1 | Hiring the services of an external agency to conduct post procurement audit for 2010-13 (GT) 12* | Proposed | SSS (Extension of existing contract ) | 2 | Prior Review | 28.11.11 | N.A. | N.A. | 21.12.11 | 21.01.12 | 28.01.12 | N.A. | 05.02.12 | 13.02.12 | 28.02.12 | 31.03.13 |
|  |  | Current Status |  |  |  | 12.04.12 | NA | NA | 15.05.12 | 15.06.12 | 22.06.12 | NA | 30.06.12 | 15.07.12 | 22.07.12 |  |
| CS – 21 / IEC1 | Production of TV Commercials on CVD, Cervical Cancer, Tribal Health and Cemonc | Proposed | LCS | 19.5/ 51 | Post Review | 01.12.11 | N.A. | N.A. | 11.12.11 | 11.01.12/12.01.12 | 12.01.12 | N.A. | 14.01.12/ 20.01.12 | N.A. |  | 07.01.11 |
|  |  | Current Status |  |  |  |  |  |  |  |  |  |  |  |  |  | completed |
| Year 1:(2010-11) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| CS – 22 / IEC2 | Designing, Execution and Deployment of IEC Print media materials on programmes of TNHSP. ( CVD, Cervical Cancer, Tribal Health and Cemonc ) | Proposed | QCBS | 9.03 | Prior Review | 25.12.10 | 02.01.11 | 28.02.11 | 07.03.11 | 12.04.11 | 25.04.11 | 30.04.11 | 07.05.11 | 15.05.11 | 31.05.11 |  |
|  |  | Current Status |  |  |  | Request for change in procurement methodology |  |
| CS – 23 / IEC3 | Designing,Execution and Deployment of IEC Display materials/Outdoor materials on programmes of TNHSP.( CVD, Cervical Cancer, Tribal Health and Cemonc ) | Proposed | QCBS | 18.03 | Prior Review | 30.12.10 | 07.01.11 | 05.03.11 | 12.03.11 | 17.04.11 | 01.05.11 | 06.05.11 | 12.05.11 | 20.05.11 | 05.06.11 |  |
|  |  | Current Status |  |  |  | Request for change in procurement methodology |  |
| CS – 24 / IEC4 | Designing , Production and Broadcasting of Radio and TV Commercials on programmes of TNHSP. | Proposed | QCBS | 35.38 | Prior Review | 05.01.11 | 12.01.11 | 10.03.11 | 17.03.11 | 22.04.11 | 06.05.11 | 11.05.11 | 17.05.11 | 25.05.11 | 10.06.11 |  |
|  |  | Current Status |  |  |  | 15.12.11 | 04.01.12 | 18.02.12 | 20.02.12 | 20.03.12 | 27.03.12 | 05.04.12 | 19.03.12 | 26.04.12 | 04.06.12 |  |
| CS – 25 / IEC5 | Designing and staging of street plays and design and deployment of innovative IEC strategies on various programmes of Tamil Nadu Health Systems Project | Proposed | QCBS | 10 | Prior Review | 12.01.11 | 19.01.11 | 17.03.11 | 24.03.11 | 29.04.11 | 13.05.11 | 18.05.11 | 24.05.11 | 31.05.11 | 17.06.11 |  |
|  |  | Current Status |  |  |  | 15.12.11 | 04.01.12 | 18.02.12 | 20.02.12 | 20.03.12 | 27.03.12 | 05.04.12 | 19.03.12 | 26.04.12 | 04.06.12 |  |
| CS – 26 / IEC6 | Video Documentation of Cardio Vascular Diseases | Proposed | LCS | 1.67 | Post Review | 05.01.11 | 12.01.11 | N.A. | 12.02.11 | 12.03.11 | 12.03.11 | N.A. | 27.03.11 | N.A. | 12.04.11 |  |
|  |  | Current Status |  |  |  | Remarks from IEC section and concerned program officer pending |  |
| CS – 27 / IEC7 | Video Documentation of Cancer Cervix activities | Proposed | LCS | 1.67 | Post Review | 05.01.11 | 12.01.11 | N.A. | 12.02.11 | 12.03.11 | 12.03.11 | N.A. | 27.03.11 | N.A. | 12.04.11 |  |
|  |  | Current Status |  |  |  | Remarks from IEC section and concerned program officer pending |  |
| CS – 28 / IEC8 | Video Documentation of HMIS | Proposed | LCS | 1.67 | Post Review | 05.01.11 | 12.01.11 | N.A. | 12.02.11 | 12.03.11 | 12.03.11 | N.A. | 27.03.11 | N.A. | 12.04.11 |  |
|  |  | Current Status |  |  |  | Remarks from IEC section and concerned program officer pending |  |
| Year 2:(2011-12) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| CS – 29 / IEC9 | Designing, execution and Deployment of IEC Print media materials on programmes of TNHSP. | Proposed | QCBS | 10.03 | Prior Review | 25.04.11 | 02.05.11 | 28.06.11 | 07.07.11 | 12.08.11 | 25.08.11 | 31.08.11 | 07.09.11 | 15.09.11 | 30.09.11 |  |
|  |  | Current Status |  |  |  | Request for change in procurement methodology |  |
| CS – 30 / IEC10 | Designing,Production and Deployment of IEC Display materials/Outdoor materials on programmes of TNHSP. | Proposed | QCBS | 23.03 | Prior Review | 30.4.10 | 07.05.11 | 05.07.11 | 12.07.11 | 17.08.11 | 01.09.11 | 06.09.11 | 12.09.11 | 20.09.11 | 05.12.11 |  |
|  |  | Current Status |  |  |  | Request for change in procurement methodology |  |
| CS – 31 / IEC11 | Designing, Production and Broadcasting of Radio and TV Commercials on programmes of TNHSP. | Proposed | QCBS | 35.38 | Prior Review | 05.05.11 | 12.05.11 | 10.07.11 | 17.07.11 | 22.08.11 | 06.09.11 | 11.09.11 | 17.09.11 | 25.09.11 | 10.10.11 |  |
|  |  | Current Status |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| CS – 32 / IEC12 | Designing and staging of street plays and design and deployment of innovative IEC strategies on various programmes of Tamil Nadu Health Systems Project | Proposed | QCBS | 10 | Prior Review | 12.05.11 | 19.05.11 | 17.07.11 | 24.07.11 | 29.08.11 | 13.09.11 | 18.09.11 | 24.09.11 | 31.09.11 | 17.10.11 |  |
|  |  | Current Status |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Year 3:(2012-13) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| CS – 33 / IEC13 | Designing , execution and Deployment of IEC Print media materials on programmes of TNHSP. | Proposed | QCBS | 10.03 | Prior Review | 25.04.12 | 02.05.12 | 28.06.12 | 07.07.12 | 12.08.12 | 25.08.12 | 31.08.12 | 07.09.12 | 15.09.12 | 30.09.12 |  |
|  |  | Current Status |  |  |  | Request for change in procurement methodology |  |
| CS – 34 / IEC14 | Designing, execution and Deployment of IEC Display materials/Outdoor materials on programmes of TNHSP. | Proposed | QCBS | 23.03 | Prior Review | 30.4.12 | 07.05.12 | 05.07.12 | 12.07.12 | 17.08.12 | 01.09.12 | 06.09.12 | 12.09.12 | 20.09.12 | 05.12.12 |  |
|  |  | Current Status |  |  |  | Request for change in procurement methodology |  |
| CS – 35 / IEC15 | Designing , Production and Broadcasting of Radio and TV Commercials on programmes of TNHSP. | Proposed | QCBS | 35.68 | Prior Review | 05.05.12 | 12.05.12 | 10.07.12 | 17.07.12 | 22.08.12 | 06.09.12 | 11.09.12 | 17.09.12 | 25.09.12 | 10.10.12 |  |
|  |  | Current Status |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| CS – 36 / IEC16 | Designing and staging of street plays and design and deployment of innovative IEC strategies on various programmes of Tamil Nadu Health Systems Project | Proposed | QCBS | 10 | Prior Review | 12.05.12 | 19.05.12 | 17.07.12 | 24.07.12 | 29.08.12 | 13.09.12 | 18.09.12 | 24.09.12 | 31.09.12 | 17.10.12 |  |
|  |  | Current Status |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| CS – 37 / HMIS | Establishment of State Health Data Resource Center | Proposed | QCBS | 4.5 | Prior Review | 12.05.11 | 19.05.11 | 17.07.11 | 24.07.11 | 29.08.11 | 13.09.11 | 18.09.11 | 24.09.11 | 31.09.11 | 17.10.11 |  |
|  |  | Current Status |  |  |  | Request from the concerned program section pending |  |
| CS – 38 / CVD | Engaging multiple Agencies for communication activities for work place interventions, (Factories, Industries, Establishments etc.) | Proposed | QCBS | 12.8 | Prior Review | 12.01.11 | 19.01.11 | 17.03.11 | 24.03.11 | 29.04.11 | 13.05.11 | 18.05.11 | 24.05.11 | 31.05.11 | 17.06.11 |  |
|  |  | Current Status |  |  |  | 15.12.11 | 04.01.12 | 18.02.12 | 20.02.12 | 20.03.12 | 27.03.12 | 05.04.12 | 19.03.12 | 26.04.12 | 04.06.12 |  |